## filtered
Country | Region | Primary Sector | Sub-Sector | Project Name | Link | Segment | Updated Date | Status | Specific Reason | Description | Specific Reason.1 | Work Resume | Location(specific) | Problem | Latitude | Longitude
Indonesia | East Asia and Pacific | Transport | Railways | Jakarta Bandung High-Speed Railway | https://constructionreviewonline.com/2020/04/construction-of-jakarta-bandung-high-speed-railway-resumes/ | Not available | 2020-04-01 | delayed | Covid-19 |  | budget changes, Workers and materials stuck in China | 1 | Jakarta | Construction | -6.2088 | 106.8456
Indonesia | East Asia and Pacific | ICT | ICT backbone | Palapa Ring Broadband | https://teknologi.bisnis.com/read/20200326/101/1218155/pembangunan-palapa-ring-tambahan-temui-kendala | Electricity transmission | 2020-03-26 | delayed | Covid-19 |  | need for imported devices such as Dense Wavelength Division Multiplex (DWDM) | 0 | Indonesia, Jakarta | Operation | -6.2088 | 106.8456
Philippines | East Asia and Pacific | Transport | Airports | Ninoy Aquino International Airport (Naia) Rehabilitation project | https://business.inquirer.net/292649/big-infra-projects-face-delays-due-to-covid-19 | Not available | 2020-03-16 | delayed | Covid-19 |  | less of priority to the government | 0 | MANILA, Philippines | Investment | 14.5995 | 120.9842
Philippines | East Asia and Pacific | Transport | Airports | Bulacan International Airport Project (New Manila International Airport) | https://business.inquirer.net/292649/big-infra-projects-face-delays-due-to-covid-19 | Not available | 2020-03-16 | delayed | Covid-19 |  | less of priority to the government | 0 | Bulakan, Bulacan | Unknown | 14.7943 | 120.8799
China | East Asia and Pacific | Transport | Airports | Wuhan Airport | https://www.airport-technology.com/news/covid-19-wuhan-airport-opens/ | Not available | 2020-04-08 | closed but resumed | Covid-19 | 1999 financial closure/link not about construction delay | China shut down all modes of transport to and from Wuhan city | 1 | Hubei Province, China | Unknown | 30.7378 | 112.2384
Togo | Sub-Saharan Africa | Energy | Electricity, Treatment Plant | Centrale thermique de Lome | https://www.agenceecofin.com/centrale/0603-74551-zimbabwe-le-coronavirus-ralentira-les-travaux-de-rehabilitation-de-la-centrale-de-hwange | Electricity generation | 2020-03-06 | delayed | Covid-19 |  | A significant number of staff members of the company in charge of the works are still in China | 0 | Zimbabwe, Hwange | Unknown | -18.3559 | 26.502
Nepal | South Asia | Energy | Electricity, Water Utility | Chilime Rasuwagadhi HPP | https://www.hydroreview.com/2020/03/09/coronavirus-may-significantly-delay-hydro-project-construction/#gref | Water utility without sewerage | 2020-03-09 | delayed | Covid-19 | 111-MW Rasuwagadhi Hydropower Project | absence of skilled Chinese workers | 0 | Nepal | Construction | 28.3949 | 84.124
Nepal | South Asia | Energy | Electricity, Water Utility | NEA Tanahun HPP | https://www.hydroreview.com/2020/03/09/coronavirus-may-significantly-delay-hydro-project-construction/#gref | Water utility without sewerage | 2020-03-09 | delayed | Covid-19 | 140-MW Tanahu Hydropower Project | absence of skilled Chinese workers | 0 | Located 150 km west of Kathmandu near Damauli | Construction | 27.7172 | 85.324
Indonesia | East Asia and Pacific | Energy | Electricity | Cirebon Coal-fired Power Plant | https://ekonomi.bisnis.com/read/20200326/44/1218068/virus-corona-bikin-repot-eksekusi-proyek-pltu-us131-miliar-tertunda | Electricity generation | 2020-03-26 | delayed | covid-19 | Indonesian Page with more than one projects listed | capital outlays due to labor and supply chain disruptions | 0 | West Java Province, Indonesia | Construction | -0.78927 | 113.9213
Indonesia | East Asia and Pacific | Energy | Electricity | PLTU (coal-fired power plant) Batang | https://www.idnfinancials.com/id/news/33561/power-plant-megaproject-continue-covid-outbreak | Electricity generation | 2020-04-18 | likely to be delayed | Covid-19 | employee tested positive for covid-19 and requested to stop but still continue operation | not about delay | 0
India | South Asia | Transport | Roads | Mumbai Metro One (Line 1) Project | https://www.deccanherald.com/national/covid-19-mumbai-metro-to-suspend-operations-on-sunday-816062.html | Not available | 2020-02-22 | operation suspended | Covid-19 | the operation suspended on Sunday and resumed | pushed a large number of labourers employed by Mumbai Metropolitan Region Development Authority or MMRDA back to their villages | 1 | Mumbai | Operation | 19.076 | 72.8777
Indonesia | East Asia and Pacific | Transport | Railways | Jakarta Bandung High-Speed Railway | https://global.chinadaily.com.cn/a/202003/26/WS5e7c0e74a310128217282227.html | Not available | 2020-02-26 | delayed | Covid-19 | Workers on the Jakarta-Bandung High-Speed Railway project are also unable to return to Indonesia after the Lunar New Year holiday. | Chinese workers have not been able to return to work. | 1 | Indonesia, Jakarta | Construction | -6.2088 | 106.8456
Argentina | Latin America and the Caribbean | Energy | Electricity | Loma Blanca Wind Portfolio | https://www.energiaestrategica.com/coronavirus-nuevas-medidas-de-mitigacion-afectan-el-avance-en-obras-de-proyectos-de-renovables-pero-no-la-operacion-de-parques/ | Electricity generation | 2020-03-19 | delayed | Covid-19 | (Eng. translation)For its part, from Goldwind confirmed to this medium that until yesterday there were some delays in the four wind farms that are being built in Chubut, for 250 MW: Loma Blanca I, II, III, each of 50 MW, and Loma Blanca, VI 100 MW. | delay in components import and specialized personnel | 0 | Chubut, near the city of Puerto Madryn | Construction | -42.7694 | -65.0317
India | South Asia | Energy | Electricity | 100-MW Tidong hydropower project | https://www.waterpowermagazine.com/news/newsstakraft-temporarily-halts-construction-of-tidong-and-los-lagos-projects-due-to-covid-19-7866058 | Electricity generation | 2020-04-09 | delayed | Covid-19 |  | For prevention purposes | 0 | Kinnaur District of Himachal Pradesh | Construction | 31.651 | 78.4752
Indonesia | East Asia and Pacific | Energy | Electricity | Java 7 PLTU (Coal-fired Power Plant) | https://ekonomi.bisnis.com/read/20200326/44/1218068/virus-corona-bikin-repot-eksekusi-proyek-pltu-us131-miliar-tertunda | Electricity generation | 2020-03-26 | delayed | Covid-19 | potential investment losses on 11 coal-fired power plants (PLTU) projects in Indonesia which will be delayed due to the corona virus or Covid-19 reaching US $ 13.1 billion. | capital outlays due to labor and supply chain disruptions due to the global Covid-19 pandemic | 0 | Banten province | Operation | -6.4058 | 106.064
Indonesia | East Asia and Pacific | Energy | Electricity | Bengkulu PLTU (Coal-fired Power Plant) | https://ekonomi.bisnis.com/read/20200326/44/1218068/virus-corona-bikin-repot-eksekusi-proyek-pltu-us131-miliar-tertunda | Electricity generation | 2020-03-26 | delayed | Covid-19 |  | capital outlays due to labor and supply chain disruptions due to the global Covid-19 pandemic | 0 | Bengkulu City | Operation | -3.7928 | 102.2608
Indonesia | East Asia and Pacific | Energy | Electricity | Tanjung Jati B Coal-Fired Power Plant (Units 5 & 6) | https://ekonomi.bisnis.com/read/20200326/44/1218068/virus-corona-bikin-repot-eksekusi-proyek-pltu-us131-miliar-tertunda | Electricity generation | 2020-03-26 | delayed | Covid-19 | Tanjung Jati B Coal-Fired Power Plant (Units 5 & 6) | capital outlays due to labor and supply chain disruptions due to the global Covid-19 pandemic | 0 | Jepara | Operation | -6.5827 | 110.6787
Indonesia | East Asia and Pacific | Energy | Electricity | Sumsel 1 Mine mouth Power Plant | https://ekonomi.bisnis.com/read/20200326/44/1218068/virus-corona-bikin-repot-eksekusi-proyek-pltu-us131-miliar-tertunda | Electricity generation | 2020-03-26 | delayed | Covid-19 |  | capital outlays due to labor and supply chain disruptions due to the global Covid-19 pandemic | 0 | South Sumatra | Operation | -3.3194 | 103.9144
Indonesia | East Asia and Pacific | Energy | Electricity | Sumsel 8 Mine mouth Power Plant | https://ekonomi.bisnis.com/read/20200326/44/1218068/virus-corona-bikin-repot-eksekusi-proyek-pltu-us131-miliar-tertunda | Electricity generation | 2020-03-26 | delayed | Covid-19 |  | capital outlays due to labor and supply chain disruptions due to the global Covid-19 pandemic | 0 | South Sumatram, Tanjung Enim mine | Operation | -3.7587 | 103.7913
Indonesia | East Asia and Pacific | Energy | Electricity | Kaltengseng 1 PLTU | https://ekonomi.bisnis.com/read/20200326/44/1218068/virus-corona-bikin-repot-eksekusi-proyek-pltu-us131-miliar-tertunda | Electricity generation | 2020-03-26 | delayed | Covid-19 |  | capital outlays due to labor and supply chain disruptions due to the global Covid-19 pandemic | 0 | gudang seng | Operation | -2.2182 | 115.2867
Indonesia | East Asia and Pacific | Energy | Electricity | Kalbar 1 PLTU | https://ekonomi.bisnis.com/read/20200326/44/1218068/virus-corona-bikin-repot-eksekusi-proyek-pltu-us131-miliar-tertunda | Electricity generation | 2020-03-26 | delayed | Covid-19 |  | capital outlays due to labor and supply chain disruptions due to the global Covid-19 pandemic | 0 | East Kalimantan | Operation | 0.53866 | 116.4194
Indonesia | East Asia and Pacific | Energy | Electricity | Nagan Raya PLTU Units 3 and 4 | https://ekonomi.bisnis.com/read/20200326/44/1218068/virus-corona-bikin-repot-eksekusi-proyek-pltu-us131-miliar-tertunda | Electricity generation | 2020-03-26 | delayed | Covid-19 |  | capital outlays due to labor and supply chain disruptions due to the global Covid-19 pandemic | 0 | Unknown | Unknown | 35.2205 | -80.8575
Indonesia | East Asia and Pacific | Energy | Electricity | Sulbagut 1 PLTU | https://ekonomi.bisnis.com/read/20200326/44/1218068/virus-corona-bikin-repot-eksekusi-proyek-pltu-us131-miliar-tertunda | Electricity generation | 2020-03-26 | delayed | Covid-19 |  | capital outlays due to labor and supply chain disruptions due to the global Covid-19 pandemic | 0 | Gorontalo Province, North Sulawesi Indonesia | Construction | 0.69994 | 122.4467
Indonesia | East Asia and Pacific | Energy | Electricity | Sulbagut 3 Power Plant | https://ekonomi.bisnis.com/read/20200326/44/1218068/virus-corona-bikin-repot-eksekusi-proyek-pltu-us131-miliar-tertunda | Electricity generation | 2020-03-26 | delayed | Covid-19 |  | capital outlays due to labor and supply chain disruptions due to the global Covid-19 pandemic | 0 | Gorontalo Province | Investment | 0.69994 | 122.4467
Sri Lanka | South Asia | Transport | Ports | Sri Lanka Port City Colombo project | https://global.chinadaily.com.cn/a/202003/26/WS5e7c0e74a310128217282227.html | Other | 2020-03-26 | delayed | Covid-19 |  | Chinese workers travel restrictions | 0 | Colombo | Construction | 6.9271 | 79.8612
Bangladesh | South Asia | Transport | Roads | Padma Multipurpose Bridge Project | https://thefinancialexpress.com.bd/trade/coronavirus-outbreak-construction-of-padma-bridge-impeded-1583122117 | Highway | 2020-03-02 | delayed | Covid-19 |  | Chinese workers travel restrictions | 0 | Padma Bridge, Approach Road, City of Mawa | Construction | 23.4779 | 90.2661
Bangladesh | South Asia | Transport | Railways | Padma Bridge Rail Link Project | https://www.dhakatribune.com/bangladesh/nation/2020/03/06/padma-bridge-rail-link-project-coronavirus-among-other-issues-hindering-progress | Highway | 2020-03-06 | delayed | Covid-19 |  | Chinese workers travel restrictions, material import delays, land acquistion delays | 0 | Padma Bridge, Approach Road, City of Mawa | Construction | 23.4779 | 90.2661
Colombia | Latin America and the Caribbean | Transport | Roads | Toyo Tunnel | https://www.elcolombiano.com/antioquia/este-es-el-plan-para-reactivar-las-obras-de-infraestructura-locales-ML12809072 | Highway and tunnel | 2020-04-14 | delayed | Covid-19 | planned to resume |  | 0
Colombia | Latin America and the Caribbean | Transport | Roads | Autopista Rio Magdalena 2 | https://www.medellinherald.com/antioquia/infrastructure | Highway | 2020-04-16 | delayed | Covid-19 | planned to resume |  | 0 | Antioquia | Construction | 7.1986 | -75.3412
Colombia | Latin America and the Caribbean | Transport | Railways | Bogota metro line 1 project | https://www.infrapppworld.com/update/bogota-metro-line-1-project-postponed-due-to-covid-19 | Regional Passenger | 2020-04-17 | delayed | Covid-19 | financing agreement signed on June 24. https://www.bbva.com/en/bbva-and-china-harbour-engineering-company-limited-sign-green-guarantee-facility-to-build-the-bogota-subway/ | affected by coronavirus quarantine orders | 0 | Bogota | Construction | 4.711 | -74.0721
Bolivia | Latin America and the Caribbean | Energy | Electricity | Ivirizu hydro plant | https://www.bnamericas.com/en/news/bolivia-pushes-back-geothermal-call | Electricity generation | 2020-03-27 | delayed | Covid-19 |  | country lockdown | 0 | Alta Cuenca of the Ivirizu River | Construction | -17.4942 | -65.2755
Bolivia | Latin America and the Caribbean | Energy | Electricity | Laguna Colorada geothermal project | https://www.bnamericas.com/en/news/bolivia-pushes-back-geothermal-call | Electricity generation | 2020-03-27 | delayed | Covid-19 |  | quarantine due to the coronavirus | 0 | Sol de Ma√±ana | Construction | -22.4341 | -67.7562
Peru | Latin America and the Caribbean | Transport | Ports | south dock of Callao port | https://www.fitchsolutions.com/corporates/infrastructure-project-finance/peruvian-port-sector-set-see-construction-uptick-though-risks-rising-15-04-2020?fSWebArticleValidation=true&mkt_tok=eyJpIjoiTTJKaFpEUTRZV0l5T1RBNSIsInQiOiJHV0JtVk0yeUR6MlpBUnRSSnZsZTJLVW1ZdDFzM2JmSWVoYzBVNTE0SzU0N2JvUTBJR0hhMnNKdmJyVkZpXC9TbXlUd1lYVWdya1FXWGtxODFUUzVhQU5cL1ZxWVhYcU1MeGt6aFBPZE52VnZkV3NHXC9VYklrV0dISEV3V2tYUytiVSJ9 | Not available | 2020-04-15 | likely to be delayed | Covid-19 | We do note challenges to the advance of port projects in Peru from the Covid-19 pandemic which will disrupt construction activity over the short term and risks slowing project development over the longer term. Through to the end of April 2020, government restrictions on construction activity will limit construction works on ongoing projects. Peru‚Äôs government on March 16 announced national isolation policies including major restrictions on construction activity. Currently these measures are set to remain in force until April 26, though we note the potential for a further extension of measures either at the national or regional levels. Additionally, we note the potential for weakened macroeconomic conditions both in Peru and globally to weigh on investor confidence in Peru‚Äôs infrastructure market. Weakened confidence, in turn, could negatively impact the advance of new projects, leading to delays, changes in project scope or cancellations. | government restrictions on construction activity | 0 | Muelle Sur del Callao | Construction | -12.0562 | -77.1503
Peru | Latin America and the Caribbean | Transport | Ports | Salaverry Multipurpose Port Terminal | https://www.fitchsolutions.com/corporates/infrastructure-project-finance/peruvian-port-sector-set-see-construction-uptick-though-risks-rising-15-04-2020?fSWebArticleValidation=true&mkt_tok=eyJpIjoiTTJKaFpEUTRZV0l5T1RBNSIsInQiOiJHV0JtVk0yeUR6MlpBUnRSSnZsZTJLVW1ZdDFzM2JmSWVoYzBVNTE0SzU0N2JvUTBJR0hhMnNKdmJyVkZpXC9TbXlUd1lYVWdya1FXWGtxODFUUzVhQU5cL1ZxWVhYcU1MeGt6aFBPZE52VnZkV3NHXC9VYklrV0dISEV3V2tYUytiVSJ9 | Not available | 2020-04-15 | likely to be delayed | Covid-19 | We do note challenges to the advance of port projects in Peru from the Covid-19 pandemic which will disrupt construction activity over the short term and risks slowing project development over the longer term. Through to the end of April 2020, government restrictions on construction activity will limit construction works on ongoing projects. Peru‚Äôs government on March 16 announced national isolation policies including major restrictions on construction activity. Currently these measures are set to remain in force until April 26, though we note the potential for a further extension of measures either at the national or regional levels. Additionally, we note the potential for weakened macroeconomic conditions both in Peru and globally to weigh on investor confidence in Peru‚Äôs infrastructure market. Weakened confidence, in turn, could negatively impact the advance of new projects, leading to delays, changes in project scope or cancellations. | government restrictions on construction activity | 0 | Department of Trujillo | Construction | -8.106 | -79.033
Colombia | Latin America and the Caribbean | Transport | Railways | Regiotram de Occidente rail project | https://www.fitchsolutions.com/infrastructure-project-finance/colombia-transport-infrastructure-expansion-faces-challenges-covid-19-03-04-2020 | Terminal | 2020-04-03 | likely to be delayed | Covid-19 | The developing coronavirus outbreak in the country, with 1,161 coronavirus cases confirmed as of April 2, will weaken transport infrastructure project development over both the short and longer-term, limiting the growth of Colombia‚Äôs construction industry overall below potential over the next several years. | social distancing policies enacted by the national government | 0 | Bogota to Fatatativa | Construction
Colombia | Latin America and the Caribbean | Transport |  | La Linea Tunnel project | https://www.fitchsolutions.com/infrastructure-project-finance/colombia-transport-infrastructure-expansion-faces-challenges-covid-19-03-04-2020 https://www.bnamericas.com/en/news/colombia-looks-to-resume-infra-works-despite-covid-19 https://tunnelbuilder.com/News/Colombia-postponement-of-the-opening-of-the-La-Linea-tunnel.aspx | Tunnel | 2020-04-03 | likely to be delayed | Covid-19 | Over the short term, we expect major disruption to road infrastructure development in the country, as social distancing measures are leading to stoppages of construction on the large number of road projects currently in the construction phase including the 4G road concession projects, the La Linea Tunnel project and a number of smaller works. | slowdown in work imposed by the Coronavirus pandemic | 0 | Cajamarca in Tolima and Calarca in Quindio | Operation | 4.5267 | -75.641
China | East Asia and Pacific | Transport | Railways, Roads | Belt and Road Initiative (BRI) (including multiple projects) | https://www.fitchsolutions.com/infrastructure-project-finance/global-covid-19-pandemic-significant-short-term-hit-chinas-belt-and-road-ambitions-08-04-2020 | Not available | 2020-04-08 | likely to be delayed | Covid-19 | The ongoing Covid-19 pandemic will cause significant delays in the progress of several Belt and Road Initiative (BRI) infrastructure projects in the short-term. | restrictions on movement | 0 | multiple | Construction | 41.8829 | -87.6493
Philippines | East Asia and Pacific | Energy | Electricity | Dinginin power plant | https://business.mb.com.ph/2020/02/24/covid-19-delays-comml-operations-of-dinginin-power-plant/ | Electricity generation | 2020-02-24 | delayed | Covid-19 |  | Chinese engineers can't fly because of Covid-anchored travel ban | 0 | Freeport Area of Bataan, Mariveles, Bataan, Philippines | Construction | 14.4399 | 120.4989
Philippines | East Asia and Pacific | Energy | Electricity | Baatan coal plant | https://www.philstar.com/business/2020/03/18/2001646/bataan-coal-plant-completion- delayed | Electricity generation | 2020-03-18 | delayed | Covid-19 |  | virus outbreak | 0 | ‚ÄéMariveles, Bataan | Construction | 14.4929 | 120.5049
Philippines | East Asia and Pacific | Energy | Electricity | Bulacan solar project | https://www.pv-tech.orq/news/coronavirus-delays-135mw-of-solar-by-philippines-utility https://www.pv-tech.org/news/coronavirus-delays-135mw-of-solar-by-philippines-utility | Electricity generation | 2020-02-25 | delayed | Covid-19 |  | Chinese engineers can't reach site because of travel bans | 1 | Luzon provinces of Tarlac and Bulacan | Construction | 15.447 | 120.4696
Nigeria | Sub-Saharan Africa | Energy | Electricity | Mambilla Hydropower Plant | https://www.dailytrust.com.ng/covid-19-may-delay-start-of-mambilla-project.html | Electricity generation | 2020-02-22 | likely to be delayed | Covid-19 |  | not specified | 0 | Kakara Village, Taraba State, Nigeria | Construction | 6.8257 | 11.1213
Philippines | East Asia and Pacific | Energy | Electricity | Tarlac solar Project | https://www.pna.gov.ph/articles/1094786 | Electricity generation | 2020-02-25 | delayed | Covid-19 |  | photovoltaic panels from China are not yet shipped out | 0 | Tarlac City, Philippines | Construction | 15.4755 | 120.5963
Kenya | Sub-Saharan Africa | Transport | Roads | Sh160 billion 87km Nairobi-Mau Summit road | https://www.the-star.co.ke/business/kenya/2020-04-16-multi--billion-road-projects-take-a-hit-as-workers-stay-home/ | Not available | 2020-04-16 | delayed | Covid-19 |  | budget cuts to avail funds for the fight against coronavirus | 0 | connecting the capital city of Nairobi, in Nairobi County, with the towns of Naivasha, Nakuru and Mau Summit, in Nakuru County | Construction | -1.2921 | 36.8219
Kenya | Sub-Saharan Africa | Transport | Roads | Sh62 billion JKIA-Westlands Expressway | https://www.msn.com/en-xl/news/other/multi-billion-road-projects-take-a-hit-as-workers-stay-home/ar-BB12HJaK | Highway | 2020-04-16 | delayed | Covid-19 | being constructed by the China Road and Bridge Corporation (CRBC) | budget cuts to avail funds for the fight against coronavirus | 0 | Jomo Kenyatta International Airport to the neighborhood of Rironi, in Kiambu County, along the Nairobi-Limuru Road | Construction | -1.3227 | 36.9261
Indonesia | East Asia and Pacific | Energy | Electricity | Sokoria Geothermal Power Plant (PLTP) | https://www.thinkgeoenergy.com/covid-19-situation-delaying-renewable-energy-development-in-indonesia/ | Electricity generation | 2020-04-26 | delay | Covid-19 | 5 MW in Ende Regency, East Nusa Tenggara (NTT) originally targeted to be operational in February 2020, but now it is estimated to shift to 2021 | massive spread of the corona virus | 0 | Sokoria, East Ndona, Ende Regency, East Nusa Tenggara, Indonesia | Construction | -8.7939 | 121.7737
Indonesia | East Asia and Pacific | Transport | Railways | Tangguh LNG Train 3 expansion project | https://www.spglobal.com/platts/en/market-insights/latest-news/natural-gas/040320-covid-19-hits-indonesia-upstream-projects-lng-exports-production-targets-sources | Electricity generation | 2020-04-03 | delay | Covid-19 | adding a third processing train with a capacity of 3.8 million mt/year, is likely to miss its deadline for starting operations in the third quarter of 2021 due to the coronavirus pandemic as some workers were asked to go home until further notice, a person with knowledge of the situation said. has already been delayed by one year from its original deadline and the first cargo may now commence at the end of the fourth quarter of 2021 | some workers were asked to go home until further notice | 0 | West Papua, Indonesia | Construction
Indonesia | East Asia and Pacific | Transport | Electricity | Kalbar-2 power station | https://industri.kontan.co.id/news/jadwal-operasional-pembangkit-terganggu-wabah-corona-ini-tanggapan-pln?page=all | Electricity generation | 2020-03-08 | potentially delayed | Covid-19 |  | obstruction of supply and raw material for plant components | 0 | Bintang Mas, Kubu Raya regency, West Kalimantan, Indonesia | Construction
Indonesia | East Asia and Pacific | Energy | Electricity | Sulut-3 power station | https://industri.kontan.co.id/news/jadwal-operasional-pembangkit-terganggu-wabah-corona-ini-tanggapan-pln?page=all | Electricity generation | 2020-03-08 | potentially delayed | Covid-19 | The two units are postponed to 2023 and 2024 in the 2018-2027 PT PLN long-range plan. The two units are postponed to 2024 and 2025 in the 2019-2028 long-range plan. | obstruction of supply and raw material for plant components | 0 | Kema village, Kema district, North Sulawesi Province, Indonesia | Construction | 1.3274 | 125.0564
Pakistan | South Asia | Energy | Electricity | Thar Block 2 power plant | https://www.eco-business.com/news/the-shadow-of-the-coronavirus-on-pakistan/ | Electricity generation | 2020-02-02 | minor delay | Covid-19 | Chinese workers cannot come back | Chinese workers cannot come back | 0 | Tharparkar district, Sindh, Pakistan | Construction | 24.8777 | 70.2408
Nigeria | Sub-Saharan Africa | Energy | Natural Gas | Obiafu-Obrikom-Oben Pipeline | https://www.offshore-technology.com/comment/oil-and-gas-pipeline-projects-delay/ | Natural gas transmission | 2020-04-14 | delayed | Covid-19 | unable to ship equipment to construction site | contractor company is unable to ship equipment from port to the construction site due to the Covid-19 pandemic | 0 | Nigeria | Construction | 9.082 | 8.6753
Vietnam | East Asia and Pacific | Energy | Electricity | Duy√™n H·∫£i-2 power station | https://www.gem.wiki/Duyen_Hai_Power_Generation_Complex | Electricity generation | 2020-03-06 | delayed | Covid-19 | On March 6, 2020 it was reported that construction of Duy√™n H·∫£i-2 would be impacted by COVID-19 and that its estimated completion date of 2021 might be delayed. | coronavirus | 0 | Dan Thanh commune, Duy√™n H·∫£i district, Tr√† Vinh province, Vietnam | Construction
Nepal | South Asia | Energy | Electricity, Water Utility | 54 MW Super Dordikhola Hydropower Project ‚ÄòB‚Äô | https://risingnepaldaily.com/business/lockdown-halts-construction-of-9-hydro-projects-in-lamjung | Electricity generation | 2020-03-30 | Paused | Covid-19 | Completely halted for the last seven days. | supply of construction raw materials has been obstructed due to the lockdown | 0 | Lamjung district | Construction | 28.2765 | 84.3542
Nepal | South Asia | Energy | Electricity, Water Utility | 25 MW Upper Dordi ‚ÄòA‚Äô Project | https://risingnepaldaily.com/business/lockdown-halts-construction-of-9-hydro-projects-in-lamjung | Electricity generation | 2020-03-30 | Paused | Covid-19 | Completely halted for the last seven days. | supply of construction raw materials has been obstructed due to the lockdown | 0 | Lamjung district | Construction | 28.2765 | 84.3542
Nepal | South Asia | Energy | Electricity, Water Utility | 12 MW Dordi-1 Project | https://risingnepaldaily.com/business/lockdown-halts-construction-of-9-hydro-projects-in-lamjung | Electricity generation | 2020-03-30 | Paused | Covid-19 | Completely halted for the last seven days. | supply of construction raw materials has been obstructed due to the lockdown | 0 | Lamjung district | Construction | 28.2765 | 84.3542
Nepal | South Asia | Energy | Electricity, Water Utility | 27 MW Dordikola Hydropower Project | https://risingnepaldaily.com/business/lockdown-halts-construction-of-9-hydro-projects-in-lamjung | Electricity generation | 2020-03-30 | Paused | Covid-19 | Completely halted for the last seven days. | supply of construction raw materials has been obstructed due to the lockdown | 0 | Lamjung district | Construction | 28.2765 | 84.3542
Nepal | South Asia | Energy | Electricity | 30 MW Nyadi Hydropower Project | https://risingnepaldaily.com/business/lockdown-halts-construction-of-9-hydro-projects-in-lamjung | Electricity generation | 2020-03-30 | delayed | Covid-19 | Disturbed due to the lockdown | Chinese workers who went home to celebrate New Year got trapped there due to the spread of coronavirus. | 0 | Nyadi Khola of Nyadi River at Bahundanda VDC of Lamjung district, in Western Nepal. | Construction | 28.3434 | 84.4225
Nepal | South Asia | Energy | Electricity | 40.27 MW Upper Nyandi Hydropower Project | https://risingnepaldaily.com/business/lockdown-halts-construction-of-9-hydro-projects-in-lamjung | Electricity generation | 2020-03-30 | delayed | Covid-19 | Disturbed due to the lockdown |  | 0
Nepal | South Asia | Energy | Electricity | 2.4 MW Upper Syange Khola | https://risingnepaldaily.com/business/lockdown-halts-construction-of-9-hydro-projects-in-lamjung | Electricity generation | 2020-03-30 | delayed | Covid-19 | according to local people, obstructed | shut down after the enforcement of lockdown to control the spread of coronavirus (COVID-19) in the country. | 0 | Taghring (Lamjung) | Construction | 28.41 | 84.38
Nepal | South Asia | Energy | Electricity | 7.7 MW Midimkhola | https://risingnepaldaily.com/business/lockdown-halts-construction-of-9-hydro-projects-in-lamjung | Electricity generation | 2020-03-30 | delayed | Covid-19 | according to local people, obstructed |  | 0
Indonesia | East Asia and Pacific | Transport | Railways | Jakarta MRT phase 2 | https://www.intellasia.net/mrt-jakarta-delays-phase-2-construction-amid-covid-19-outbreak-777762 | Local Passenger/Light rail | 2020-05-02 | delayed | Covid-19 | The COVID-19 outbreak has forced city-owned transportation company PT MRT Jakarta to postpone construction of phase 2 of the Jakarta MRT. | it is not possible for the contractor to work in the current circumstances | 0 | extending 6.3 kilometers from Bundaran HI to Kota in West Jakarta, commence project: 2.8 km underground tunnel from Bundaran HI to the National Monument (Monas) in Central Jakarta | Construction | -6.1754 | 106.8272
India | South Asia | Transport | Airports | Kempegowda International Airport terminal 2 expansion | https://www.business-standard.com/article/companies/fairfax-india-foresees-delay-in-bangalore-airport-expansion-due-to-covid-19-120050500657_1.html | Terminal | 2020-05-05 | expected to delay | Covid-19 | suspension of construction activities are expected to delay the completion of the first phase of the Terminal-2 expansion of Bangalore International Airport Limited | lockdown and revenue hit drastically due to shortfall of passengers | 0 | KIAL Rd, Devanahalli, Bengaluru, Karnataka 560300, India | Construction | 13.1991 | 77.7065
Myanmar | East Asia and Pacific | Transport | Roads | Yangon Elevated Expressway | https://thailand-construction.com/myanmars-yangon-elevated-expressway-project-delayed-for-two-months-due-to-covid-19/ | Highway | 2020-05-09 | delayed | Covid-19 | The tender process for the Yangon Elevated Expressway has been suspended for two months due to COVID-19. The Yangon Elevated Expressway will be implemented by the Ministry of Construction and Yangon Region Government under a Public Private Partnership with the winning bidder. | main foreign investors roll back investment | 0 | yangon, myanmar | Investment | 16.8409 | 96.1735
Turkey | Europe and Central Asia | Transport | Ports | Istanbul Salipazari (Galataport) Cruise Port | https://globaldata.com/turkish-construction-industry-growth-forecast-revised-down-as-covid-19-worsens-economic-outlook/ |  | 2020-04-29 | delayed | Covid-19 | There have been reports of disruption to several construction sites in Turkey, including the US$1.7bn Galataport development, where workers have been protesting following the death of a construction worker who contracted COVID-19. The contractors in charge of the project have agreed to shut down the site until 3rd May following the protests. | workers have been protesting following the death of a construction worker who contracted COVID-19 | 0 | shores of the Galata, Karakoy and Tophane | Construction | 41.0262 | 28.9735
Bolivia | Latin America and the Caribbean | Energy | Electricity | 100MW Laguna Colorada geothermal project | https://www.bnamericas.com/en/news/bolivia-geothermal-project-latest-pandemic-casualty | Electricity generation | 2020-03-06 | delayed | Covid-19 | excess generation, durplus and the need to prioritize resources to tackle Covid-19 | government declared a nationwide quarantine on March 22 that currently runs through May 10. | 0 | Sol de Ma√±ana geothermal field, Laguna Colorada | Investment | -22.4341 | -67.7562
Bosnia and Herzegovina | Europe and Central Asia | Energy | Electricity | 160 MW hydro power plant (HPP) HE Dabar | https://seenews.com/news/coronavirus-to-delay-dabar-hpp-project-in-bosnias-serb-republic-report-689960 | Electricity generation | 2020-03-06 | delayed | Covid-19 | signing of the contract delayed | been delayed by a month due to the coronavirus outbreak in China | 0 | southern town of Trebinje | Construction
Zimbabwe | Sub-Saharan Africa | Energy | Electricity | Hwange Thermal Power Station Expansion | https://www.theindependent.co.zw/2020/04/10/covid-19-derails-us14bn-worth-zim-china-projects/ | Electricity generation | 2020-04-10 | delayed | Covid-19 | US$1,1 billion Hwange Thermal Power Station upgrading | disrupted by the pandemic, with huge construction shipments delayed as the world races to find a solution to contain Covid-19. | 0 | Hwange District, Matabeleland North Province | Construction | -18.8537 | 26.6082
Zimbabwe | Sub-Saharan Africa | Transport | Airports | Robert Mugabe International Airport expansion | https://www.theindependent.co.zw/2020/04/10/covid-19-derails-us14bn-worth-zim-china-projects/ | Runway and terminal | 2020-04-10 | delayed | Covid-19 | US$153 million Robert Mugabe International Airport expansion | disrupted by the pandemic, with huge construction shipments delayed as the world races to find a solution to contain Covid-19. | 0 | Harare, Zimbabwe | Construction | -17.8252 | 31.0335
Zimbabwe | Sub-Saharan Africa | Energy | ICT backbone | NetOne expansion | https://www.theindependent.co.zw/2020/04/10/covid-19-derails-us14bn-worth-zim-china-projects/ | Land-base cable | 2020-04-10 | delayed | Covid-19 | US$70 million NetOne expansion | disrupted by the pandemic, with huge construction shipments delayed as the world races to find a solution to contain Covid-19. | 0 |  | Construction
Tunisia | Middle East and North Africa | Energy | Electricity | Nawara gas field development project | https://www.meed.com/covid-19-delays-work-on-tunisian-gas-project | Electricity generation | 2020-04-05 | delayed | Covid-19 | technical intervention delayed |  | 0 | governorates of Tataouine, K√©bili, Mednine and Gabes. | Construction
Bhutan | South Asia | Energy | Electricity | the Nu 93.75 billion Punatsangchu-I project | https://www.orfonline.org/research/south-asia-weekly-65697/ | Electricity generation | 2020-03-06 | delayed | Covid-19 | Owing to shortages of manpower and raw materials, two India-Bhutan inter-governmental hydropower projects under construction ‚Äî the Nu 93.75 billion Punatsangchu-I project and Nu 72.90 billion Punatsangchu II project are impacted the outbreak of COVID-19 from 6th March and also the ongoing lockdown in India. | Owing to shortages of manpower and raw materials, lockdown of India | 0 | Punatsangchhu River | Construction
Nigeria | Sub-Saharan Africa | Transport | Airports | Abuja international airports | https://www.reuters.com/article/health-coronavirus-nigeria-transport/nigeria-to-shut-lagos-abuja-international-airports-from-monday-idUSL8N2BE0KO | Not available | 2020-03-23 | shut | Covid-19 | shut two terminals of international airports as the number of corona cases doubled | restrictions aimed at preventing the spread of the coronavirus | 0 |  | Operation
Indonesia | East Asia and Pacific | Transport | Roads | Serang-Panimbang toll road | https://finance.detik.com/infrastruktur/d-4987481/proyek-konstruksi-tol-serang-panimbang-disetop | Highway | 2020-04-22 | delayed | Covid-19 |  | worker suspected of contracting COVID-19 | 0 | Banten | Construction | -6.4058 | 106.064
Philippines | East Asia and Pacific | Transport | Roads | Harbor Link R10 section | https://ppp.gov.ph/in_the_news/mptc-to-resume-work-on-major-projects/ | Highway | 2020-03-18 | resume | Covid-19 | resumed early last week | due to the COVID-19 pandemic and community quarantine | 1 | from the port of Manila and North Luzon Expressway | Construction | 14.5833 | 120.95
Philippines | East Asia and Pacific | Transport | Roads | Cebu Cordova Link Expressway. | https://ppp.gov.ph/in_the_news/mptc-to-resume-work-on-major-projects/ | Highway | 2020-03-18 | resume | Covid-19 | resumed early last week | the implementation of the community quarantine | 0 | linking Cebu City and Cordova | Construction | 10.2835 | 123.8808
Philippines | East Asia and Pacific | Transport | Roads | Cavite-Laguna Expressway (CALAX) | https://ppp.gov.ph/in_the_news/mptc-to-resume-work-on-major-projects/ | Highway | 2020-03-18 | resume | Covid-19 | would restart this week | the implementation of the community quarantine | 0 | Bacoor and Kawit, Cavite areas | Construction | 14.441 | 120.9038
Philippines | East Asia and Pacific | Transport | Roads | North Luzon Expressway (NLEX) Connector | https://ppp.gov.ph/in_the_news/mptc-to-resume-work-on-major-projects/ | Highway and tunnel | 2020-05-18 | resume | Covid-19 | would restart this week | the implementation of the community quarantine | 0 | NCR REGION - NATIONAL CAPITAL REGION | Construction | 28.402 | 76.826
Philippines | East Asia and Pacific | Transport | Roads | Subic Freeport Expressway (SFEx) | https://www.bworldonline.com/nlex-corp-restarts-construction-activities/ | Highway and tunnel | 2020-05-18 | resume | Covid-19 | would resumre by this week | disruption caused by the coronavirus pandemic | 0 | the provinces of Zambales and Bataan | Construction | 14.6417 | 120.4818
India | South Asia | Transport | Roads | chardham all-weather road project | https://economictimes.indiatimes.com/news/economy/infrastructure/covid-19-chardham-all-weather-road-project-to-be-delayed-due-to-lockdown/articleshow/75176701.cms | Highway | 2020-03-23 | delayed | Covid-19 | delayed by nearly six months due to the shortage of labourers amid the ongoing lockdown | COVID-19 lockdown | 0 | Uttarakhand state | Construction | 30.0668 | 79.0193
India | South Asia | Transport | Roads | Malhar Road project | https://economictimes.indiatimes.com/small-biz/productline/building-materials/ludhiana-smart-city-projects-hit-roadblock-thanks-to-covid-19/articleshow/75118864.cms | Highway | 2020-04-13 | delayed | Covid-19 | as soon as the lockdown was announced, it stopped immediately. The deadline for the project will get extended according to the curfew period. | COVID-19 lockdown | 0 | linking Pakhowal Road and Ferozepur Road | Construction | 30.9023 | 75.8321
India | South Asia | Transport | Railways, Roads | Kanpur Metro construction | https://www.livemint.com/news/india/kanpur-metro-construction-work-resumes-amid-lockdown-3-0-11589020714033.html | Not available | 2020-05-09 | resume | Covid-19 | The work has resumed after the Ministry of Home Affairs (MHA) allowed a range of economic activities to begin | COVID-19 lockdown | 1 | Kanpur metropolitan area | Construction | 26.3334 | 80.4104
Nepal | South Asia | Transport | Airports | Gautam Buddha International Airport (GBIA) | https://www.nepalisansar.com/government/nepal-resumes-gbia-airport-construction-amid-covid-19/ | Not available | 2020-05-13 | resume | Covid-19 | resume the construction work of the Gautam Buddha International Airport (GBIA) amid the rise in COVID-19 cases | COVID-19 lockdown | 1 | serving the Siddharthanagar municipality in Rupandehi District in Province No. 5 in Nepal | Construction | 27.5065 | 83.4377
Nepal | South Asia | Water and sewerage | Water Utility | Melamchi Water Supply Project | https://kathmandupost.com/valley/2020/04/06/melamchi-likely-to-face-more-delays-as-workers-leave-the-site | Water utility with swerage | 2020-04-06 | delayed | Covid-19 | An engineer working with the Chinese contractor told the Post that the delay might be of a minimum two months. | COVID-19 lockdown | 0 | Melamchi, Nepal | Construction | 27.8297 | 85.5762
Bulgaria | Europe and Central Asia | Energy | Electricity | Bulgaria‚Äôs Belene nuclear power plant | https://www.intellinews.com/coronavirus-outbreak-to-delay-launch-of-bulgaria-s-belene-project-181811/ | Electricity generation | 2020-04-24 | delayed | Covid-19 | delay of the tender due to the coronavirus outbreak. launch of the tender would depend on the easing of restrictions the government has imposed since March 13 when it declared a state of emergency. The government in Sofia hopes to finish the project within 10 years at a cost of up to ‚Ç¨10bn. | Coronavirus outbreak | 0 | 3 km from Belene and 11 km from Svishtov in Pleven Province | Construction | 43.6184 | 25.3506
Ecuador | Latin America and the Caribbean | Transport | Railways, Roads | Quito Metro project | https://www.construccionlatinoamericana.com/metro-de-quito-paralizado-por-coronavirus/142852.article | Not available | 2020-03-17 | halts | Covid-19 | Work on the underground Metro in Quito, Ecuador, has been suspended until measures are taken to guarantee the safety of the 2,000 workers on the project. | COVID-19 lockdown | 0 | Quito, the capital of Ecuador | Construction | -0.18065 | -78.4678
Montenegro | Europe and Central Asia | Transport | Roads | Bar-Boljare(Belgrade) motorway (A-1 motorway) | https://adreskaradag.com/karadag-otoyolunda-son-durum/ | Highway | 2020-05-09 | delayed | Covid-19 | Due to the coronavirus epidemic, the contractor Chinese company CRBC asked for additional time and payment at the Bar-Boljara stage earlier this week. | COVID-19 lockdown | 0 | From Belgrade to Bar | Construction
India | South Asia | Transport | Railways | Kochi Metro‚Äôs Thykoodam-Pettah corridor | https://www.thehindu.com/news/cities/Kochi/metro-work-resumes/article31417634.ece | Local Passenger/Light rail | 2020-04-23 | delayed | Covid-19 | All civil, signalling and telecommunication works on the 1.5-km-long corridor was halted on March 22 following the lockdown. | covid lockdown | 1 | Pettah metro station | Construction | 6.9368 | 79.8525
Philippines | East Asia and Pacific | Transport | Roads | BGC-Ortigas Center Link Road | https://www.philstar.com/headlines/2020/05/17/2014564/dpwh-resumes-work-ncr-flagship-projects | Highway | 2020-05-17 | delayed but resumed | Covid-19 | For the BGC-Ortigas Center Link Road Project, the DPWH and project contractors have agreed to adopt a catch up plan to make up for the months-long delay in construction activities. | onset of the COVID-19 pandemic | 1 | both sides of the Pasig River | Construction | 14.5689 | 121.0318
Philippines | East Asia and Pacific | Transport | Roads | Estrella-Pantaleon Bridge Project connecting Makati City and Mandaluyong City | https://www.philstar.com/headlines/2020/05/17/2014564/dpwh-resumes-work-ncr-flagship-projects | Highway | 2020-05-17 | delayed but resumed | Covid-19 | Construction activities have also restarted for the Estrella-Pantaleon Bridge Project connecting Makati City and Mandaluyong City and the Binondo-Intramuros Bridge in Manila, which are 54 percent and 32 percent complete, respectively. | prevent COVID-19 contagion | 1 | connecting Makati City and Mandaluyong City | Construction | 14.5794 | 121.0359
Philippines | East Asia and Pacific | Transport | Roads | Binondo-Intramuros Bridge | https://www.philstar.com/headlines/2020/05/17/2014564/dpwh-resumes-work-ncr-flagship-projects | Highway | 2020-05-17 | delayed but resumed | Covid-19 | Construction activities have also restarted for the Estrella-Pantaleon Bridge Project connecting Makati City and Mandaluyong City and the Binondo-Intramuros Bridge in Manila, which are 54 percent and 32 percent complete, respectively. | prevent COVID-19 contagion | 1 | construction bridge in Manila, Philippines that spans the Pasig River | Construction | 14.5995 | 120.9842
India | South Asia | Energy | Electricity | 200 megawatts (MW) ACME Solar | https://www.reuters.com/article/india-solar/citing-covid-uncertainty-indias-acme-solar-cancels-deal-to-supply-power-at-record-low-tariff-idUSL4N2D22TL | Electricity generation | 2020-05-20 | canceled | Covid-19 | ACME cited land acquisition delays, the coronavirus outbreak and its impact on suppliers of solar cells and modules in China and delay in setting up of transmission networks as reasons for terminating the contract under ‚Äúforce majeure‚Äù. | land acquisition delays, the coronavirus outbreak and its impact on suppliers of solar cells and modules in China and delay in setting up of transmission networks | 0 | the northwestern state of Rajasthan | Construction | 27.0238 | 74.2179
Thailand | East Asia and Pacific | Transport | Railways | high-speed railway 250km section between Hua Lamphong station and Nakhon Ratchasima | http://www.globalconstructionreview.com/news/chinas-plans-southeast-asia-suffer-coronavirus-sho/ | Local Passenger/Light rail | 2020-05-06 | delayed | Covid-19 | A package of 14 contracts for the 250km section between Hua Lamphong station in Bangkok (pictured) and the northeastern town of Nakhon Ratchasima was to have been agreed in May, but this has now been put back to October. | due to the ongoing COVID-19 pandemic | 0 | between Bangkok and Nakhon Ratchasima | Construction
Mexico | Latin America and the Caribbean | Energy | Electricity | El Llano Solar Power Plant | https://renews.biz/60174/covid-19-neoen-shuts-down-375mw-el-lano-in-mexico/ | Electricity generation | 2020-05-08 | shut down | Covid-19 | Neoen has shut down its 375MW El Lano solar project in Mexico after the government suspended testing for wind and PV projects due to COVID-19. | Llano Solar Farm has stopped sending power to the grid in Mexico after the country‚Äôs system operator Centro Nacional de Control de Energia (CENACE) issued a ruling to this effect owing to COVID-19 | 0 | d 20km east of the town of Aguascalientes, state of Aguascalientes, in the center of Mexico | Operation | 21.8853 | -102.2916
Myanmar | East Asia and Pacific | Transport | Railways | Muse-Mandalay railway link | http://www.globalconstructionreview.com/news/chinas-plans-southeast-asia-suffer-coronavirus-sho// | Regional Passenger | 2020-05-08 | delayed | Covid-19 | In Myanmar, a massive programme of infrastructure work for the China-Myanmar Economic Corridor (CMEC) has been hit by the coronavirus. This work includes a $9bn Muse-to-Mandalay railway link, and plans valued at around $10bn to build a deep sea port, power stations and industrial parks at Kyaukpyu. | There are some places [in Shan State] that are not accessible to the study due to security concerns | 0 | 31km (268 miles) long and pass through armed conflict areas in Shan State | Investment | 22.0362 | 98.1339
Myanmar | East Asia and Pacific | Energy |  | Kyaukphyu special economic zone (sea port, power stations and industrial parks) | http://www.globalconstructionreview.com/news/chinas-plans-southeast-asia-suffer-coronavirus-sho/ | Other | 2020-05-08 | delayed | Covid-19 | In Myanmar, a massive programme of infrastructure work for the China-Myanmar Economic Corridor (CMEC) has been hit by the coronavirus. This work includes a $9bn Muse-to-Mandalay railway link, and plans valued at around $10bn to build a deep sea port, power stations and industrial parks at Kyaukpyu. | few Chinese managers, technicians or tourists are showing up | 0 | between Hua Lamphong station in Bangkok Kyaukphyu, Ramree Island, Rakhine State | Construction | 13.7563 | 100.5018
Myanmar | East Asia and Pacific | Transport | Railways | East Coast Rail Link (ECRL) | https://www.straitstimes.com/asia/se-asia/malaysia-gives-green-light-for-construction-to-resume-on-east-coast-rail-link | Local Passenger/Light rail | 2020-02-27 | delayed but resumed | Covid-19 | The RM44 billion (S$14.3 billion) project was suspended when movement restrictions were put in place on March 18 in Malaysia to curb the spread of the coronavirus. | movement control order (MCO) imposed and its construction was back to normal | 1 | Kuantan, Malaysia | Construction | 3.7634 | 103.2202
Brazil | Latin America and the Caribbean | Energy | Electricity | 1,400MW Angra-3 nuclear power plant | https://www.devdiscourse.com/article/international/1062323-covid-19-to-delay-brazil-nuclear-plant--eletronuclear | Electricity generation | 2020-05-22 | delayed | Covid-19 | Lower demand for electricity and a currency slide during the coronavirus crisis will push completion of Brazil's third nuclear reactor into 2027 | public engagement in the process will not begin until the planning inspectorate accepts the application which takes around a month, suspend producing electricity in the wake of the plunge in demand following the coronavirus outbreak | 0 | Central Nuclear Almirante √Ålvaro Alberto (CNAAA) on the Itaorna Beach in Angra dos Reis, Rio de Janeiro, Brazil | Construction | -23.0075 | -44.4574
Myanmar | East Asia and Pacific | Energy | Electricity | 350MW LNG power plant in Thanlyin in Yangon | https://frontiermyanmar.net/en/chinese-consortium-may-avoid-fines-despite-missing-emergency-power-deadline | Electricity generation | 2020-02-27 | delayed | Covid-19 | Due to travel restrictions and commercial flight bans, the power generation equipment, and the machinery and experts required to install it, were unable to reach Myanmar by the original deadlines. | (soon to be resumed) | 0 | Thanlyin, Southeast Yangon | Construction
Myanmar | East Asia and Pacific | Energy | Electricity | 400-MW LNG power plant in Thaketa in Yangon | https://frontiermyanmar.net/en/chinese-consortium-may-avoid-fines-despite-missing-emergency-power-deadline | Electricity generation | 2020-02-27 | delayed | Covid-19 | Due to travel restrictions and commercial flight bans, the power generation equipment, and the machinery and experts required to install it, were unable to reach Myanmar by the original deadlines. | (soon to be resumed) | 0 | Thaketa, Yangon | Construction
Myanmar | East Asia and Pacific | Energy | Electricity | 150-MW LNG power plant in Kyaukphyu in Rakhine State | https://frontiermyanmar.net/en/chinese-consortium-may-avoid-fines-despite-missing-emergency-power-deadline | Electricity generation | 2020-02-27 | delayed | Covid-19 | delayed due to the shutdown of a factory producing LNG tank containers in Wuhan | likely to be delayed until at least September | 0 | Kyaukphyu in Rakhine State, Yangon | Construction
India | South Asia | Transport | Airports | Navi Mumbai International Airport | https://www.businessinsider.in/business/news/navi-mumbai-airport-construction-to-be-little-delayed-amid-coronavirus-pandemic/articleshow/75477515.cms | Runway and terminal | 2020-04-30 | delayed | Covid-19 | little bit delayed due to the situation arising out of the coronavirus pandemic | covid lockdown | 0 | Ulwe, Pargaon Dungi, Maharashtra 410206, India | Construction
Indonesia | East Asia and Pacific | Transport | Roads | Brebes-Tegal Ring Road in Central Java | https://www.thejakartapost.com/news/2020/04/23/covid-19-crisis-delays-several-infrastructure-projects.html | Highway | 2020-04-23 | delayed | Covid-19 | The budget changes will also cause a delay in several other projects, such as the development of the Way Sekampung Dam in Lampung, the Jragung Dam in Central Java, the Temef Dam in East Nusa Tenggara, the Kuningan East Ring Road in West Java and the construction of the Brebes Ring Road in Central Java. | budget change due to covid 20 | 0 | (ÏïÑÏßÅ Î™®Î¶Ñ) | Investment
Indonesia | East Asia and Pacific | Transport | Railways | Rapid Transit System(RTS) Link (Johor Bahru‚ÄìSingapore Rapid Transit System) | https://www.reuters.com/article/malaysia-singapore-railway/malaysia-and-singapore-delay-deal-on-rail-project-to-end-july-idUSL4N2CK03M | Local Passenger/Light rail | 2020-05-02 | delayed | Covid-19 | Malaysia and Singapore agreed to extend the deadline for three months. | hit by curbs on movement to stem the coronavirus | 0 | Johor Bahru, Johor, Malaysia, Woodlands, Singapore | Construction
Mexico | Latin America and the Caribbean | Transport | Railways | Maya Train project | https://mexiconewsdaily.com/news/new-injunction-halts-maya-train-construction-in-3-chiapas-municipalities/ | Local Passenger/Light rail | 2020-05-09 | delayed | Covid-19 | A court in Chiapas has issued a provisional suspension order against the Maya Train project, halting construction in three municipalities due to coronavirus concerns. | Indigenous residents argued that construction could increase their risk of being exposed to Covid-19 | 0 | Yucat√°n Peninsula, Mexico | Construction
Sri Lanka | South Asia | Energy | Electricity | Uma Oya hydroelectric power plant | http://www.china.org.cn/world/Off_the_Wire/2020-04/29/content_75991315.htm | Electricity generation | 2020-04-29 | delayed but resumed | Covid-19 | Sri Lanka will complete construction of a 230 GWh hydroelectric power plant by October after delays caused by the COVID-19 lockdown. | resumed (Eighty-five Iranians arrived in Sri Lanka to work on the Uma-Oya project) | 1 | Uva Province, Sri Lanka | Construction
Bangladesh | South Asia | Energy | Electricity | Southwest Transmission Grid Expansion Project | https://www.dhakatribune.com/bangladesh/power-energy/2020/05/12/ongoing-power-transmission-projects-hit-snag-for-corona-shutdown | Electricity transmission | 2020-05-12 | delayed | Covid-19 | The PGCB official said although coronavirus situation in China has improved, Chinese officials and workers, especially the technicians, are yet to come back as the situation in Bangladesh has been deteriorating. | missing workers due to covid 19 | 0 |  | Construction
Bangladesh | South Asia | Energy | Electricity | 500 MW HVDC Back-to-Back Station at Comilla North | https://www.dhakatribune.com/bangladesh/power-energy/2020/05/12/ongoing-power-transmission-projects-hit-snag-for-corona-shutdown | Electricity transmission | 2020-05-12 | delayed | Covid-19 | The PGCB official said although coronavirus situation in China has improved, Chinese officials and workers, especially the technicians, are yet to come back as the situation in Bangladesh has been deteriorating. | Neither the Chinese workers, nor the equipment are coming from China since the pandemic hit Wuhan | 0 | Cumilla North, Bangladesh | Construction
India | South Asia | Transport | Railways | Kolkata Metro Railway East-West project | https://www.ndtv.com/india-news/coronavirus-india-kolkata-east-west-metro-corridor-work-to-recommence-soon-official-2222606 | Regional Passenger | 2020-05-02 | suspended | Covid-19 | Work for the 16.6-km-long rapid transit system, connecting the twin cities of Kolkata and Howrah, came to a halt after a nationwide lockdown was imposed by the Union government to control the COVID-19 pandemic. | resumed (Workers who had returned home were brought back after Unlock 1 and their health condition was checked before allowing them to join duty) | 1 | Kolkata Metropolitan Area, India | Construction | 22.6592 | 88.3628
Zambia | Sub-Saharan Africa | Energy | Electricity | Batoka Gorge hydroelectric project | https://www.afrik21.africa/en/zambia-towards-surplus-electricity-production-from-renewable-energies/ | Electricity generation | 2020-05-06 | may be delayed | Covid-19 | They are expected to start work in the last quarter of 2020. This prospect may be impacted by Covid-19. | (ÌôïÏã§Ìûà ÎØ∏Î§ÑÏßÑ Í±¥ ÏïÑÎãò) | 0 | planned to be on the Zambezi River across the International border between Zambia and Zimbabwe | Construction | -15.6385 | 29.5736
Albania | Europe and Central Asia | Transport | Airports | Vlora Airport/ Vlor√´ International Airport | https://www.intellinews.com/tender-process-for-vlora-airport-in-albania-to-resume-soon-182432/ | Runway and terminal | 2020-05-04 | delayed but resumed | Covid-19 | 12 days remain for international companies to file bids in a tender, which was suspended in late March due to the coronavirus (COVID-19) pandemic. The tender process for the construction and operation of Vlora airport in Albania will resume soon, local media reported citing the infrastructure minister | postponed the deadline to submit offer for potential investors regarding the Vlora Airport concession, amid the COVID-19 crisis | 1 | Akerni, Albania | Investment | 40.6022 | 19.4482
India | South Asia | Energy | Electricity | 1600MW thermal project in Jharkhand | https://energy.economictimes.indiatimes.com/news/power/1600-mw-jharkhand-project-delayed-due-to-lockdown-adani-power/76146784 | Electricity generation | 2020-06-02 | delayed | Covid-19 | The project has been delayed due to the coronavirus-induced lockdown. | delayed the schedule of implementation and commission | 0 | sector-specific SEZ for power at villages -- Motia, Mali, Gaighat and adjacent villages in Godda district, Jharkhand | Construction | 26.7807 | 86.641
Nepal | South Asia | Energy | Electricity | 465MW Upper Tamakoshi Hydroelectric Project | https://myrepublica.nagariknetwork.com/news/upper-tamakoshi-project-likely-to-be-delayed/ | Electricity generation | 2020-05-25 | delayed | Covid-19 | The completion of the Upper Tamakoshi Hydro Electric Project (UTHEP) is likely to be delayed as a result of the COVID-19 lockdown in the country. The mega project is likely to miss its deadline because of the lack of construction materials, manpower and equipment. | he supply of construction materials like cement and chemicals is not smooth and equipment from India have not been brought to Nepal, complicating the work,‚Äù said Ganesh Prasad Neupane, spokesperson for the project, ‚ÄúHydromechanical parts and equipment are still stuck in the factories at Kolkata and also the project is facing the lack of manpower. | 0 | Tamakoshi River in Dolakha district in north central Nepal | Construction | 27.6509 | 86.0879
Angola | Sub-Saharan Africa | Transport | Ports | Port of Luanda Multipurpose Terminal | https://www.porttechnology.org/news/tender-for-angolas-largest-port-pushed-back-due-to-covid-19-pandemic/ | Terminal | 2020-06-04 | commission bidding extended | Covid-19 | extended the deadline for concession bids for the Port of Luanda Multipurpose Terminal | due to the crisis brought on by the pandemic, which has severely restricted movement across the globe and caused businesses to amend plans. | 0 | Luanda Province | Investment | -9.0351 | 13.2663
Nigeria | Sub-Saharan Africa | Transport | Airports | Akanu Ibiam International Airport | https://www.sunnewsonline.com/work-resumes-at-enugu-airport/ | Runway and terminal | 2020-06-02 | suspended-resumed | Covid-19 | Sirika said this in his official Twitter handle yesterday (Monday) that despite the lockdown and closure of airports over COVID-19, work has resumed at the Enugu Airport | covid-19 lockdown just like other projects around the country as the disease halt the global economy. | 1 | capital city of Enugu State of Nigeria | Construction | 6.5364 | 7.4356
Myanmar | East Asia and Pacific | Transport | Airports | Falam(Surbung) Airport | https://consult-myanmar.com/2020/06/05/opening-of-the-first-airport-in-myanmars-chin-state-delayed-amid-covid-19/ | Runway and terminal | 2020-06-05 | delayed | Covid-19 | The runway, the control tower and the airport buildings are all complete. The test landing will take place this month. However, due to COVID-19 restrictions and the weather, we cannot say yet when the airport will begin full operations, | Since there are travel restrictions, the opening is being delayed and we cannot tell when the airport will begin its operations,‚Äù U Soe Paing, the director of the Department of Aviation, told The Irrawaddy. ‚ÄúIt all depends on the COVID-19 situation and Union government decisions. Opening delayed buy construction completed | 0 | Falam, Chin state | Construction | 22.9142 | 93.675
Montenegro | Europe and Central Asia | Energy | Electricity | Velje brdo PV plant | https://balkangreenenergynews.com/velje-brdo-pv-plant-tender-to-start-by-year-end-could-expand-to-300-mw/ | Electricity generation | 2020-06-17 | delayed | Covid-19 | The coronavirus pandemic has delayed the announcement of the tender, planned for the third quarter of the year | the announcement of the tender and the lease of land for the construction of the solar power plant were planned for the third quarter. The coronavirus pandemic‚Äôs impact warranted the delay, | 0 | Podgorica | Investment | 42.4304 | 19.2594
Malaysia | East Asia and Pacific | Transport | Railways | Kuala Lumpur‚ÄìSingapore high-speed rail | https://www.wionews.com/world/malaysia-singapore-defer-high-speed-rail-project-until-year-end-302147 | Regional Passenger | 2020-05-31 | delayed | Covid-19 | Malaysia has agreed with neighbouring Singapore to suspend until December 31 a project for a high-speed rail link between the capital, Kuala Lumpur. | deferment of project due to high costs and covid-19 cicuit breaker | 0 | Kuala Lumpur, Malaysia to Singapor | Construction
Malaysia | East Asia and Pacific | Transport | Airports | Penang International Airport | https://www.dfnionline.com/latest-news/penang-international-airport-expansion-project-may-postponed-due-covid-19-29-05-2020/ | Runway and terminal | 2020-05-29 | likely to be delayed | Covid-19 | Work to expand the Penang International Airport (PIA) could be delayed due to the disruption caused by the current pandemic, Chief Minister Chow Kon Yeow said. | if the pandemic continues, the airport will not be optimally used. | 0 | Penang Malaysia | Construction | 5.4164 | 100.3327
Nigeria | Sub-Saharan Africa | Transport | Railways | Lagos ‚Äì Ibadan standard-gauge line : Ibadan ‚Äì Kano section | https://www.railjournal.com/africa/nigerian-rail-projects-delayed-by-covid-19/ | Local Passenger/Light rail | 2020-06-16 | delayed | Covid-19 | Covid-19 has also delayed the start of construction of the Ibadan ‚Äì Kano section, which was originally scheduled to begin in June or July. | plan was interfered by the rise of the COVID-19 virus | 0 |  | Construction
Sri Lanka | South Asia | Energy | Treatment plant | Sri Lanka waste-to-energy power plant in Colombo | https://economynext.com/sri-lanka-waste-to-energy-power-plant-delayed-by-covid-19-travel-curbs-70837/ | Incineration / Waste to Energy | 2020-06-09 | delayed | Covid-19 | A waste-to-energy plant being built north of Sri Lanka‚Äôs capital Colombo has been delayed due to Coronavirus travel restriction which had blocked the arrival of specialists from China, a minister said. | Coronavirus travel restriction which had blocked the arrival of specialists from China | 0 | Muthurajawela in Sri Lanka | Construction | 7.0789 | 79.853
Congo, Dem. Rep. | Sub-Saharan Africa | Energy | Electricity | $52 million solar photovoltaic power plant in Kisangani | https://globalpressjournal.com/africa/democratic-republic-of-congo/coronavirus-claims-another-victim-solar-power-plant-drc/ | Electricity generation | 2020-05-24 | delayed | Covid-19 | But the proposed 12-month construction project that was scheduled to begin in January has fallen victim to the same scourge that is stalking individuals, communities and countries around the world: the coronavirus pandemic. | suspended amid fears surrounding the coronavirus | 0 | Kisangani | Construction | 0.51853 | 25.2008
Colombia | Latin America and the Caribbean | Energy | Electricity | Hidroituango mega-dam project | https://www.bnamericas.com/en/news/covid-19-delays-colombias-hidroituango-mega-dam-project | Electricity generation | 2020-06-12 | delayed | Covid-19 | Colombia's Empresa's P√∫blicas de Medell√≠n (EPM) has postponed the planned completion of its troubled Hidroituango project to 2022 as it grapples with a coronavirus outbreak among workers. | forced EPM to drastically reduce its workforce at the site. The company has said that 295 employees have been infected, one of whom has been hospitalized. | 0 | Ituango | Construction | 7.1722 | -75.7644
Vietnam | East Asia and Pacific | Transport | Railways | C√°t Linh-H√† ƒê√¥ng urban elevated railway | https://vietnamnews.vn/economy/653729/safety-assessment-of-cat-linh-ha-dong-urban-railway-to-be-completed-soon.html | Regional Passenger | 2020-03-17 | delayed | Covid-19 | Trial delayed as Chinese experts cannot go back to Vietnam, it is still delayed (06.25) | 100 Chinese experts could not return to Vi·ªát Nam following China's lockdown order to deal with the COVID-19 outbreak | 0 | √°t Linh in Ba ƒê√¨nh district to the suburban district of H√† ƒê√¥ng | Construction | 21.0371 | 105.8227
India | South Asia | Energy | Electricity | 624MW Kiru hydroelectric project in Kishtwar distric | https://www.dailyexcelsior.com/finally-work-on-624-mw-kiru-hep-to-begin-next-month/ | Electricity generation | 2020-05-23 | delayed | Covid-19 | before the companies could start mobilizing men and machinery lockdown was imposed in the entire country in order to contain COVID-19 pandemic. | before the companies could start mobilizing men and machinery lockdown was imposed in the entire country in order to contain COVID-19 pandemic | 0 | Kiru / Pathrnakki in district Kishtwar | Construction | 33.3382 | 75.9427
Bangladesh | South Asia | Energy | Railways | Dhaka Mass Rapid Transit Line 6 | https://bdnews24.com/economy/2020/06/14/coronavirus-crisis-derails-bangladesh-metrorail-project | Local Passenger/Light rail | 2020-06-14 | delayed | Covid-19 | Bangladesh's Japan-financed metro rail project for the capital Dhaka, already delayed by a 2016 terror attack on a cafe, may not be ready for its partial launch in late 2021 due to the coronavirus pandemic. | shipment of the first set of coaches from Japan has been delayed | 0 | central Dhaka | Construction | 23.7797 | 90.4153
Malaysia | East Asia and Pacific | Transport | Roads | Sungai Krian and Batang Saribas bridge projects | https://www.malaymail.com/news/malaysia/2020/06/11/construction-of-bridges-in-sarawak-to-resume-after-covid-19-delays-says-cm/1874589 | Highway | 2020-06-11 | delayed but resumed | Covid-19 | The bridge projects for Sungai Krian and Batang Saribas have resumed construction after being delayed for three months as a result of the Covid-19 pandemic as well as the implementation of the movement control order (MCO) and the conditional movement control order (CMCO). | implementation of the movement control order (MCO) and the conditional movement control order | 1 | Batang Krian and Batang Saribas in Pusa district | Construction
Afghanistan | South Asia | Transport | Roads | Yakawlang Road Project | http://www.afghanistantimes.af/construction-projects-stagnate-in-bamyan-amid-covid-19/ | Regional Passenger | 2020-06-24 | delayed | Covid-19 | The government has stopped Bamyan‚Äôs main road and construction projects because of the coronavirus pandemic and its implications. | The engineers, who were working on the projects, are in China. According to initial founds, their visas applications have been denied | 0 | central province of Bamyan | Construction | 34.81 | 67.8212
India | South Asia | Transport | Railways | Mumbai Metro lines 2A and 7 | https://thelogicalnews.com/2020/06/09/covid-19-crisis-delays-work-on-mumbai-metro-lines-2a-and-7/ | Regional Passenger | 2020-06-09 | delayed | Covid-19 | Amid coronavirus crisis, completion of Mumbai‚Äôs most awaited Metro lines 2A and 7 is likely to get delayed by at least 3-4 months more than the original estimated time due to the disruption in the work. | large number of migrant workers employed by Mumbai Metropolitan Region Development Authority or MMRDA have returned to their villages. | 0 | Mumbai | Construction | 19.076 | 72.8777
India | South Asia | Transport | Airports | Kempegowda International Airport (KIA) Terminal 2 | https://www.deccanherald.com/city/top-bengaluru-stories/kia-second-terminal-infra-expansion-to-be-delayed-by-6-12-months-844802.html | Regional Passenger | 2020-06-02 | delayed | Covid-19 | navailability of labour has also been attributed to the delay in Terminal-2 (T2). ‚ÄúT2 (Phase 1) was originally scheduled for completion by April 1, 2021. There will be a 6-12 months delay. The road works within the airport will also be delayed," | Labourers gone home | 0 | Karnataka, | Construction | 15.3173 | 75.7139
Kazakhstan | Europe and Central Asia | Energy | Electricity | 50MW Kostanay Wind Farm | https://www.ichongqing.info/2020/05/27/chinas-production-resumption-drives-belt-and-road-cooperation-fuels-global-growth/ | Electricity generation | 2020-05-26 | delayed but resumed | Covid-19 | The resumption of work at the wind farm, like many other cooperation projects | Hundreds of Chinese and Kazakh workers are binding reinforced steel bars to erect the wind farm‚Äôs giant turbine foundations before early July. shipment of wind turbines | 1 | Kostanay Region | Construction | 51.5077 | 64.0479
Kenya | Sub-Saharan Africa | Transport | Roads | Lamu Port-South Sudan-Ethiopia Transport Corridor | https://theconversation.com/with-construction-paused-lets-rethink-roads-and-railway-projects-to-protect-people-and-nature-137672 |  | 2020-06-15 | delayed | Covid-19 | Kenyan President Uhuru Kenyatta fumed at construction delays on the Lamu Port-South Sudan-Ethiopia Transport Corridor in 2019 ‚Äì a US$22 billion (¬£18 billion) transport network that includes a 32-berth port, highways, railways and pipelines. | Lockdown restrictions and the uncertainty caused by COVID-19 have made sourcing labour and materials more difficult, increasing construction costs. The result is that infrastructure building has slowed globally | 0 | Lamu Kenya | Construction | -2.2696 | 40.9006
Jamaica | Latin America and the Caribbean | Transport | Airports | development of Norman Manley International Airport (NMIA) | http://www.jamaicaobserver.com/news/st-elizabeth-aerodrome-airstrip-to-get-attention_195596?profile=1432 | Runway and terminal | 2020-06-05 | delayed | Covid-19 | He added that a master plan airport expansion programme, estimated at US$100 million, was slated to commence this year, but has been pushed back as a result of the coronavirus pandemic. | commencement delayed due to covid | 0 | Kingston, | Construction | 44.2312 | -76.486
Bangladesh | South Asia | Transport | Airports | Shah Amanat International Airport in Chattogram | https://tbsnews.net/economy/aviation/covid-19-chattogram-airports-runway-strengthening-work-stalled-98896 | Runway and terminal | 2020-06-27 | delayed | Covid-19 | Due to the novel Coronavirus outbreak, work on the runway capacity enhancement project at Shah Amanat International Airport in Chattogram has been stalled. | construction firms have yet to start the work due to Covid-19. | 0 | Southwest of Chattogram | Construction | 22.3569 | 91.7832
Cambodia | East Asia and Pacific | Energy | Electricity | 400MW oil power plant in Kandal province | https://thailand-construction.com/cambodias-power-plant-in-kandal-province-delayed-by-covid-19-travel-bans/ | Electricity generation | 2020-06-24 | delayed | Covid-19 | The first phase of a $380 million heavy fuel oil power plant in Kandal province‚Äôs Lvea Em district has been further delayed due to travel restrictions imposed to curve Covid-19, a Ministry of Mines and Energy senior official told The Post. | because the technicians ‚Äì from Finland and Germany ‚Äì cannot fly to Cambodia | 0 | Kandal Province, Lvea Em district | Construction | 11.5454 | 105.0411
Bulgaria | Europe | Energy | Treatment plant | Belene nuclear power plant | https://intellinews.com/coronavirus-outbreak-to-delay-launch-of-bulgaria-s-belene-project-181811/ | Natural gas transmission | 2020-04-26 | delayed | Covid-19 | The coronavirus (COVID-19) pandemic will delay the tender to select a company to build Bulgaria‚Äôs Belene nuclear power plant, TASS reported on April 24. | Despite the Covid-19 crisis, the procedure for construction of Belene nuclear power plant has not stopped even for a moment, Bulgaria‚Äôs Minister of Energy Temenuzhka Petkova said in Parliament. | 0 | River Danube near the town of Belene | Investment | 43.6445 | 25.1246